# Pilot Review - Meeting Notes

Week 4 | Simulated Portfolio Case Study

| Date | Facilitator | Participants | Purpose |
| --- | --- | --- | --- |
| Mar 16, 2026 | Project Coordinator | Registration, Revenue Cycle, Nursing, IT Apps, Clinical Ops | Review pilot performance, defects, and full-rollout readiness |

# Agenda

Registration-time trend

Wait-time trend

Digital-form adoption

Pilot defects

Eligibility queue

Clinical handoff

RAID and change review

# Discussion Summary

Pilot departments showed meaningful reductions in registration and wait time. The main technical issue was a duplicate guarantor-field mapping, which was corrected and scheduled for regression testing. Operational leaders confirmed that the intake readiness checklist improved handoff consistency.

# Decisions

| Decision ID | Decision | Owner | Date |
| --- | --- | --- | --- |
| DEC-04 | Proceed with full rollout after regression test passes | Clinical Operations Lead | Mar 16, 2026 |
| DEC-05 | Retain assisted digital station in Emergency Intake | Registration Manager | Mar 16, 2026 |
| DEC-06 | Use daily eligibility queue threshold through stabilization | Revenue Cycle Lead | Mar 16, 2026 |

# Action Items

| Action | Owner | Due | Status |
| --- | --- | --- | --- |
| Retest guarantor field mapping | IT Applications Lead | Mar 17, 2026 | Complete |
| Publish final standard-work guide | Project Coordinator | Mar 18, 2026 | Complete |
| Confirm training completion by department | Training Lead | Mar 18, 2026 | Complete |
| Update executive dashboard with pilot exit results | Project Coordinator | Mar 18, 2026 | Complete |