# Hospital Intake Workflow Optimization

Project Charter & Management Plan | Simulated Portfolio Case Study

Data disclosure: All data is simulated. This project contains no PHI or real patient information.

# 1. Executive Summary

This project coordinates a simulated hospital intake workflow optimization across registration, insurance verification, digital intake, and clinical handoff. The objective is to reduce processing delays, lower rework, improve data quality, and standardize intake across five departments.

# 2. Business Need

The current-state workflow includes duplicated intake information, late insurance verification, inconsistent handoffs, and exception handling that occurs too late. These conditions create avoidable wait time and rework.

# 3. Objectives

Reduce average registration time by at least 40%; reduce average wait time by at least 35%; increase digital form adoption to at least 90%; reduce simulated data-entry errors below 3%; improve patient satisfaction to at least 4.3/5; complete all milestones; close all critical risks/issues; and remain within the $105,000 baseline.

# 4. Scope

In scope: As-Is mapping, KPI baseline, To-Be design, digital intake configuration, pre-arrival eligibility workflow, staff training, pilot, QA, phased rollout, stabilization, reporting, and closeout. Out of scope: EHR replacement, clinical treatment redesign, claims adjudication, staffing model redesign, and use of real patient records.

# 5. Success Measures

| Metric | Target | Simulated Result | Status |
| --- | --- | --- | --- |
| Registration time reduction | >=40% | 48.6% | Met |
| Wait-time reduction | >=35% | 44.5% | Met |
| Digital form adoption | >=90% | 94% | Met |
| Data error rate | <3% | 1.8% | Met |
| Patient satisfaction | >=4.3/5 | 4.6/5 | Met |
| Milestone completion | 100% | 100% | Met |
| Budget | <=$105,000 | $103,150 | Met |

# 6. Workstreams & Deliverables

| Workstream | Deliverables | Primary Owner |
| --- | --- | --- |
| Governance | Charter, status cadence, decision log, closeout | Project Coordinator |
| Process Mapping | As-Is / To-Be maps, bottleneck findings | Business Analyst / Process Lead |
| Digital Intake | Form configuration, validation, mapping | IT Applications Lead |
| Eligibility | Pre-arrival insurance work queue | Revenue Cycle Lead |
| Training | Standard work, job aids, staff sessions | Training Lead |
| Pilot & QA | Pilot, defect log, readiness criteria | Project Coordinator / IT Apps |
| Rollout | Phased deployment and stabilization | Project Coordinator |
| Analytics | Operational KPI dashboard and reporting | Data Analyst / Project Coordinator |

# 7. Governance & RACI

Weekly working-team meetings reviewed tasks, dependencies, RAID, defects, and changes. Pilot-period huddles were held daily for operational exceptions. Executive updates were issued biweekly.

| Activity | Sponsor | Project Coord. | Registration | Revenue Cycle | Nursing | IT Apps |
| --- | --- | --- | --- | --- | --- | --- |
| Charter | A | R | C | C | C | I |
| As-Is mapping | I | C | R | R | R | C |
| To-Be design | I | R | C | C | C | C |
| Digital configuration | I | C | C | I | I | A/R |
| Eligibility redesign | I | C | C | A/R | I | C |
| Pilot | I | A/R | R | R | R | R |
| Full rollout | I | A/R | R | R | R | R |
| KPI reporting | I | A/R | C | C | C | C |

# 8. Schedule & Milestones

| Milestone | Baseline | Actual | Variance |
| --- | --- | --- | --- |
| Charter Approved | Feb 4, 2026 | Feb 4, 2026 | 0 days |
| As-Is Mapping Complete | Feb 9, 2026 | Feb 9, 2026 | 0 days |
| To-Be Design Approved | Feb 17, 2026 | Feb 18, 2026 | +1 day |
| Pilot Ready | Mar 7, 2026 | Mar 6, 2026 | -1 day |
| Pilot Exit | Mar 18, 2026 | Mar 18, 2026 | 0 days |
| Full Rollout Complete | Mar 29, 2026 | Mar 29, 2026 | 0 days |
| Executive Closeout | Apr 13, 2026 | Apr 13, 2026 | 0 days |

# 9. Risk & Issue Management

| ID | Item | Score | Mitigation / Resolution | Status |
| --- | --- | --- | --- | --- |
| R-01 | Digital adoption risk in Emergency Intake | 12 | Assisted digital station + staff script | Closed |
| R-02 | Eligibility backlog may shift delay upstream | 15 | Queue threshold + backup coverage | Closed |
| R-03 | Department practices may diverge | 12 | Standard work + audit checklist | Closed |
| I-01 | Duplicate guarantor mapping defect | 20 | Corrected mapping + retest | Closed |
| D-01 | Clinical leadership sign-off | 20 | Readiness review with pilot evidence | Complete |

# 10. Budget Management

| Category | Baseline | Actual | Variance |
| --- | --- | --- | --- |
| Workflow Analysis & Design | $18,000 | $17,400 | +$600 |
| Digital Intake Configuration | $26,000 | $27,150 | -$1,150 |
| Eligibility Workflow Setup | $15,000 | $14,400 | +$600 |
| Training & Change Management | $16,000 | $15,350 | +$650 |
| Pilot & QA | $12,000 | $11,800 | +$200 |
| Rollout & Stabilization | $18,000 | $17,050 | +$950 |
| TOTAL | $105,000 | $103,150 | +$1,850 favorable |

# 11. Quality & Acceptance

Acceptance criteria included validated digital-form rules, eligibility queue readiness, complete staff training, resolved critical pilot defects, standardized handoff checklist, KPI trend improvement, and executive acceptance of closeout.

# 12. Privacy & Data Handling

The portfolio artifact uses only simulated operational metrics. No patient names, dates of birth, identifiers, diagnoses, insurance numbers, encounter records, or other PHI are included.

# 13. Lessons Learned

Move insurance verification upstream only when queue ownership and exception thresholds are clear.

Real-time form validation prevents downstream rework more effectively than end-of-process review.

Pilot exit criteria should include both defect severity and operational adoption metrics.

Department-specific adoption support may be necessary even when the standardized workflow is the same.

One formula-driven dashboard reduces inconsistency between operations and executive reporting.