# Weekly Status Report - Week 6

Hospital Intake Workflow Optimization | Simulated Portfolio Case Study

| Overall | Schedule | Budget | Scope | Quality |
| --- | --- | --- | --- | --- |
| Green | Green | Green | Green | Green |

# Executive Summary

The optimized intake workflow is fully deployed across all five simulated departments and has entered closeout. Registration time, wait time, digital adoption, data quality, and patient satisfaction all exceeded the project targets, with no open RAID items.

# Key Performance Indicators

| KPI | Baseline | Current | Result |
| --- | --- | --- | --- |
| Avg registration time | 14.8 min | 7.6 min | 48.6% reduction |
| Avg patient wait | 31.0 min | 17.2 min | 44.5% reduction |
| Digital form adoption | 42% | 94% | +52 pts |
| Data error rate | 8.7% | 1.8% | 6.9 pts lower |
| Patient satisfaction | 3.7 / 5 | 4.6 / 5 | +0.9 |
| Budget | $105,000 | $103,150 | 1.8% favorable |

# Completed This Week

Completed stabilization monitoring.

Closed remaining operational issues.

Validated final KPI trends.

Completed final budget reconciliation.

Prepared executive closeout package.

# Next Steps

Deliver executive closeout update.

Archive project artifacts and decision log.

Transition KPI monitoring to operational owners.