## Weekly Metrics
Week | Invited | Registered | Attended | Completed | Attendance % | Completion % | Avg Satisfaction | Open Issues | Closed Issues | Sessions Delivered | Milestones Due | Milestones Completed
Week 1 | 180 | 165 | 154 | 145 | 93.33% | 94.16% | 4.3 | 3 | 1 | 6 | 2 | 2
Week 2 | 220 | 207 | 196 | 188 | 94.69% | 95.92% | 4.4 | 4 | 2 | 8 | 2 | 2
Week 3 | 245 | 236 | 226 | 218 | 95.76% | 96.46% | 4.5 | 3 | 3 | 9 | 2 | 2
Week 4 | 270 | 261 | 252 | 246 | 96.55% | 97.62% | 4.6 | 2 | 3 | 10 | 2 | 2
Week 5 | 300 | 292 | 283 | 278 | 96.92% | 98.23% | 4.6 | 1 | 2 | 11 | 1 | 1
Week 6 | 325 | 319 | 312 | 307 | 97.81% | 98.4% | 4.7 | 0 | 1 | 12 | 1 | 1

## Regional Rollout
Region | Target Leaders | Registered | Attended | Completed | Attendance % | Completion % | Avg Satisfaction | Sessions Planned | Sessions Delivered | Language Coverage | Status
North America | 360 | 350 | 342 | 337 | 97.71% | 98.54% | 4.7 | 12 | 12 | English / French | Complete
EMEA | 330 | 321 | 309 | 301 | 96.26% | 97.41% | 4.6 | 12 | 12 | English / French / German | Complete
APAC | 300 | 288 | 278 | 270 | 96.53% | 97.12% | 4.6 | 11 | 11 | English / Japanese | Complete
LATAM | 250 | 242 | 231 | 224 | 95.45% | 96.97% | 4.5 | 10 | 10 | English / Spanish / Portuguese | Complete

## Task Tracker
ID | Workstream | Task | Owner | Priority | Status | Start Date | Due Date | % Complete | Dependency | Days to Due | Health | Region | Notes
GL-001 | Governance | Approve program charter | Project Coordinator | High | Complete | 2026-04-06 | 2026-04-08 | 100% | None | 0 | Green | Global | Sponsor approval received
GL-002 | Curriculum | Finalize leadership curriculum | L&D Lead | Critical | Complete | 2026-04-08 | 2026-04-17 | 100% | GL-001 | 0 | Green | Global | Core modules baselined
GL-003 | Localization | Complete regional localization | Regional HR Leads | High | Complete | 2026-04-13 | 2026-04-24 | 100% | GL-002 | 0 | Green | EMEA/APAC/LATAM | Language review complete
GL-004 | Technology | Configure LMS enrollment rules | LMS Administrator | Critical | Complete | 2026-04-13 | 2026-04-22 | 100% | GL-001 | 0 | Green | Global | Automated enrollment enabled
GL-005 | Facilitators | Confirm facilitator roster | L&D Lead | High | Complete | 2026-04-15 | 2026-04-24 | 100% | GL-002 | 0 | Green | Global | Backups identified
GL-006 | Scheduling | Publish regional session calendar | Project Coordinator | Critical | Complete | 2026-04-20 | 2026-04-29 | 100% | GL-003, GL-005 | 0 | Green | Global | Time zones validated
GL-007 | Communications | Launch participant communications | HR Communications | High | Complete | 2026-04-27 | 2026-05-01 | 100% | GL-006 | 0 | Green | Global | Manager toolkit included
GL-008 | Delivery | Deliver North America cohort | Regional HR Lead | Critical | Complete | 2026-05-04 | 2026-05-15 | 100% | GL-004, GL-006, GL-007 | 0 | Green | North America | 12 sessions delivered
GL-009 | Delivery | Deliver EMEA cohort | Regional HR Lead | Critical | Complete | 2026-05-11 | 2026-05-22 | 100% | GL-004, GL-006, GL-007 | 0 | Green | EMEA | 12 sessions delivered
GL-010 | Delivery | Deliver APAC cohort | Regional HR Lead | Critical | Complete | 2026-05-18 | 2026-05-29 | 100% | GL-004, GL-006, GL-007 | 0 | Green | APAC | 11 sessions delivered
GL-011 | Delivery | Deliver LATAM cohort | Regional HR Lead | Critical | Complete | 2026-05-25 | 2026-06-05 | 100% | GL-004, GL-006, GL-007 | 0 | Green | LATAM | 10 sessions delivered
GL-012 | Reporting | Complete final evaluation and closeout | Project Coordinator | High | Complete | 2026-06-01 | 2026-06-12 | 100% | GL-008, GL-009, GL-010, GL-011 | 0 | Green | Global | Executive closeout approved
Formulas:
Days to Due = IF([Status]="Complete",0,[Due Date]-TODAY())
Health = IF([Status]="Complete","Green",IF([Due Date]<TODAY(),"Red",IF([Due Date]-TODAY()<=3,"Amber","Green")))

## Session Tracker
Session ID | Region | Cohort | Session Date | Facilitator | Capacity | Registered | Attended | Completed | Attendance % | Completion % | Satisfaction | Status
NA-01 | North America | Cohort A | 2026-05-04 | Facilitator 1 | 35 | 33 | 32 | 31 | 96.97% | 96.88% | 4.7 | Complete
NA-02 | North America | Cohort B | 2026-05-06 | Facilitator 2 | 35 | 34 | 33 | 33 | 97.06% | 100% | 4.8 | Complete
NA-03 | North America | Cohort C | 2026-05-08 | Facilitator 3 | 35 | 35 | 34 | 34 | 97.14% | 100% | 4.7 | Complete
EM-01 | EMEA | Cohort A | 2026-05-11 | Facilitator 4 | 35 | 33 | 32 | 31 | 96.97% | 96.88% | 4.6 | Complete
EM-02 | EMEA | Cohort B | 2026-05-13 | Facilitator 5 | 35 | 34 | 33 | 32 | 97.06% | 96.97% | 4.6 | Complete
AP-01 | APAC | Cohort A | 2026-05-18 | Facilitator 6 | 35 | 32 | 31 | 30 | 96.88% | 96.77% | 4.6 | Complete
AP-02 | APAC | Cohort B | 2026-05-20 | Facilitator 7 | 35 | 33 | 32 | 31 | 96.97% | 96.88% | 4.5 | Complete
LA-01 | LATAM | Cohort A | 2026-05-25 | Facilitator 8 | 35 | 32 | 31 | 30 | 96.88% | 96.77% | 4.5 | Complete
LA-02 | LATAM | Cohort B | 2026-05-27 | Facilitator 9 | 35 | 33 | 32 | 31 | 96.97% | 96.88% | 4.6 | Complete

## RAID Log
RAID ID | Type | Description | Impact | Probability | Score | Owner | Response / Mitigation | Target Date | Status | Escalation | Days to Target | Risk Level
R-01 | Risk | Regional time-zone conflicts could reduce attendance | 4 | 3 | 12 | Project Coordinator | Publish multiple session windows and recordings | 2026-04-29 | Closed | No | 0 | High
R-02 | Risk | Localization delays may affect EMEA/APAC launch dates | 5 | 3 | 15 | Regional HR Leads | Parallelize translation review and use priority content list | 2026-04-24 | Closed | Yes | 0 | Critical
R-03 | Risk | Facilitator availability may create session gaps | 4 | 3 | 12 | L&D Lead | Maintain trained backup facilitator pool | 2026-04-24 | Closed | No | 0 | High
I-01 | Issue | LMS enrollment rules omitted a manager population | 5 | 4 | 20 | LMS Administrator | Correct rule logic and reconcile participant list | 2026-04-28 | Closed | Yes | 0 | Critical
D-01 | Dependency | Regional HR sign-off required before participant communications | 4 | 4 | 16 | Regional HR Leads | Track approvals in weekly governance meeting | 2026-04-29 | Complete | Yes | 0 | Critical
Formulas:
Days to Target = IF(OR([Status]="Closed",[Status]="Complete",[Status]="Validated"),0,[Target Date]-TODAY())

## Milestones
Milestone | Baseline Date | Actual Date | Status | Days Variance | Exit Criteria | Owner | On-Time? | Schedule Performance
Program Charter Approved | 2026-04-08 | 2026-04-08 | Complete | 0 | Sponsor approval | Project Coordinator | Yes | On/Ahead
Curriculum Baseline | 2026-04-17 | 2026-04-17 | Complete | 0 | Curriculum approved | L&D Lead | Yes | On/Ahead
Localization Complete | 2026-04-24 | 2026-04-25 | Complete | 1 | Regional language review complete | Regional HR Leads | No | Minor Delay
LMS & Enrollment Ready | 2026-04-29 | 2026-04-28 | Complete | -1 | Enrollment validation passed | LMS Administrator | Yes | On/Ahead
Regional Delivery Complete | 2026-06-05 | 2026-06-05 | Complete | 0 | All cohorts delivered | Project Coordinator | Yes | On/Ahead
Executive Closeout | 2026-06-12 | 2026-06-12 | Complete | 0 | Final report accepted | Project Coordinator | Yes | On/Ahead

## Budget
Category | Baseline Budget | Actual Cost | Variance | Variance % | Forecast at Completion | Notes
Curriculum Design | 28000 | 27200 | 800 | 2.857% | 27200 | Completed below baseline
Localization & Translation | 22000 | 23150 | -1150 | -5.227% | 23150 | Additional review cycle in EMEA
LMS Configuration | 14000 | 13750 | 250 | 1.786% | 13750 | Within plan
Facilitation & Delivery | 42000 | 40800 | 1200 | 2.857% | 40800 | Virtual delivery reduced travel cost
Communications & Materials | 12000 | 11600 | 400 | 3.333% | 11600 | Digital materials reduced print cost
Evaluation & Reporting | 10000 | 9800 | 200 | 2% | 9800 | Within plan
Summary | Baseline | Actual / Forecast | Variance | Variance % | Forecast
Total | 128000 | 126300 | 1700 | 1.328% | 126300
Contingency | 10000 | 11700

## RACI & Stakeholders
Deliverable / Activity | Executive Sponsor | Project Coordinator | L&D Lead | Regional HR Leads | LMS Admin | HR Communications | Facilitators
Program charter | A | R | C | C | I | I | I
Curriculum design | I | C | A/R | C | I | I | C
Localization | I | C | C | A/R | I | I | C
LMS configuration | I | C | C | C | A/R | I | I
Regional scheduling | I | A/R | C | R | C | I | C
Participant communications | I | C | C | C | I | A/R | I
Training delivery | I | C | A | R | C | I | R
KPI reporting | I | A/R | C | C | C | I | I
Closeout / lessons learned | A | R | C | C | C | C | C
Stakeholder | Role | Influence | Interest | Communication | Cadence | Owner | Key Need
Executive Sponsor | Program sponsor | High | High | Executive update | Biweekly | Project Coordinator | Progress, risks, budget
L&D Leadership | Program owner | High | High | Working session | Weekly | Project Coordinator | Curriculum and delivery readiness
Regional HR Leads | Regional execution | High | High | Regional sync | Weekly | Project Coordinator | Schedule, localization, attendance
People Managers | Participant support | Medium | High | Manager toolkit | Before cohorts | HR Communications | Expectations and reinforcement
Participants | Learners | Low | High | Email / LMS | Per cohort | HR Communications | Schedule, access, completion

## Change Log
Change ID | Request | Reason | Impact | Decision | Decision Date | Owner | Status
CR-01 | Add a second EMEA time slot | Improve attendance across time zones | +$1,150 localization/facilitation; no launch date impact | Approved | 2026-04-20 | Project Coordinator | Implemented
CR-02 | Extend recordings from 14 to 30 days | Support participants with schedule conflicts | No material cost; improves accessibility | Approved | 2026-04-27 | L&D Lead | Implemented
CR-03 | Add manager reinforcement guide | Improve transfer of learning | Minor communications effort; no schedule impact | Approved | 2026-05-01 | HR Communications | Implemented

## Dashboard
Global Leadership Training Rollout ¦ Executive Dashboard
[5 empty] | Region | Completion % | Week | Completed | Week | Satisfaction
[5 empty] | North America | 98.54% | Week 1 | 145 | Week 1 | 4.3
Program KPI | Value | Delivery Health | Value |  | EMEA | 97.41% | Week 2 | 188 | Week 2 | 4.4
Overall Status | Green | Open Risks / Issues | 0 |  | APAC | 97.12% | Week 3 | 218 | Week 3 | 4.5
Total Target Leaders | 1240 | Open Critical RAID Items | 0 |  | LATAM | 96.97% | Week 4 | 246 | Week 4 | 4.6
Total Completed | 1132 | Sessions Delivered | 45 |  |  |  | Week 5 | 278 | Week 5 | 4.6
Overall Attendance | 96.59% | Budget Variance | 1.328% |  |  |  | Week 6 | 307 | Week 6 | 4.7
Overall Completion | 97.59% | Milestone Completion | 100%
Avg Satisfaction | 4.6 | Final Closeout Date | 2026-06-12
Executive Summary
Scope | Global leadership development rollout across North America, EMEA, APAC, and LATAM.
Delivery | 45 regional sessions delivered with localized content and facilitator coverage.
Participation | 1,132 of 1,240 targeted leaders completed the program in the simulated rollout.
Quality | Average participant satisfaction reached 4.6/5 with no open launch-blocking issues at closeout.
Schedule | Program closeout completed on the baseline date; one localization milestone finished one day late.
Budget | Final actual cost remained below the $128,000 baseline budget.
Dashboard Notes
This dashboard is built directly in Excel. KPI cards are formula-driven from Regional Rollout, RAID Log, Milestones, Budget, Weekly Metrics, and Task Tracker sheets. Native Excel charts update when underlying project data changes.
Project Controls Demonstrated
Planning & Controls |  | Delivery & Governance |  | Analytics & Reporting
Schedule baseline vs. actual Milestone variance Budget & contingency Task health and dependencies |  | RAID scoring & mitigation RACI and stakeholder cadence Change control & decision trail Regional / session coordination |  | Attendance & completion KPIs Satisfaction trend Native Excel charts Formula-driven executive reporting

## Formula Guide
Area | Formula Example | Purpose | Interview Talking Point
Regional Rollout | =D2/C2 | Calculates regional attendance rate | Shows automated participation KPI tracking.
Regional Rollout | =E2/D2 | Calculates regional completion rate | Measures completion among attendees.
Task Tracker | =IF(F2="Complete",0,H2-TODAY()) | Calculates days remaining | Supports proactive schedule monitoring.
Task Tracker | =IF(F2="Complete","Green",IF(H2<TODAY(),"Red",IF(H2-TODAY()<=3,"Amber","Green"))) | RAG health | Flags overdue or near-due work.
RAID Log | =D2*E2 | Calculates probability x impact | Standardizes risk prioritization.
Milestones | =C2-B2 | Calculates schedule variance | Shows baseline vs actual milestone performance.
Budget | =B2-C2 | Calculates cost variance | Tracks favorable/unfavorable budget performance.
Dashboard | =SUM('Regional Rollout'!E2:E5) | Aggregates program completions | Rolls source data into executive reporting.
Dashboard | =AVERAGE('Regional Rollout'!H2:H5) | Calculates overall satisfaction | Tracks learner experience at program level.