# Global Leadership Training Rollout

Project Charter & Management Plan | Simulated Portfolio Case Study

Portfolio disclosure: This is a simulated project created to demonstrate project-coordination practices. Metrics and outcomes are illustrative.

# 1. Executive Summary

A global leadership-development program is coordinated across North America, EMEA, APAC, and LATAM. The Project Coordinator supports governance, cross-functional planning, scheduling, localization, LMS readiness, communications, delivery tracking, risk management, KPI reporting, budget monitoring, and program closeout.

# 2. Business Need

The organization requires a consistent leadership-development experience across regions while accounting for language, time-zone, facilitator, and technology constraints. The initiative standardizes core leadership content while allowing controlled regional adaptation.

# 3. Objectives

Deliver a scalable global training program; achieve at least 95% attendance among registered participants; achieve at least 95% completion among attendees; maintain average satisfaction of at least 4.3/5; complete all milestones; close with no unresolved critical risks; and remain within the $128,000 baseline budget.

# 4. Scope

In scope: chartering, curriculum readiness, localization, LMS configuration, facilitator coordination, regional scheduling, participant communications, cohort delivery, attendance/completion tracking, satisfaction measurement, RAID, budget, executive reporting, and closeout. Out of scope: long-term performance-management redesign, compensation changes, and replacement of the enterprise LMS.

# 5. Success Measures

| Metric | Target | Simulated Result | Status |
| --- | --- | --- | --- |
| Attendance rate | >=95% | 96.6% | Met |
| Completion rate | >=95% | 97.6% | Met |
| Average satisfaction | >=4.3/5 | 4.6/5 | Met |
| Milestone completion | 100% | 100% | Met |
| Open critical issues at closeout | 0 | 0 | Met |
| Budget | <=$128,000 | $126,300 | Met |

# 6. Workstreams & Deliverables

| Workstream | Key Deliverables | Primary Owner |
| --- | --- | --- |
| Governance | Charter, status cadence, decisions, closeout | Project Coordinator |
| Curriculum | Core modules, facilitator materials, learning objectives | L&D Lead |
| Localization | Regional language and cultural adaptation | Regional HR Leads |
| Technology | LMS configuration, enrollment, reporting | LMS Administrator |
| Scheduling & Delivery | Regional calendars, facilitator coverage, session execution | Project Coordinator / Regional HR |
| Communications | Participant messaging, manager toolkit, reminders | HR Communications |
| Reporting | KPI dashboard, weekly status, executive updates | Project Coordinator |

# 7. Governance & RACI

Governance uses a weekly working-team meeting, weekly regional syncs during launch, and biweekly executive updates. RAID and changes are reviewed as standing agenda items.

| Activity | Sponsor | Project Coordinator | L&D | Regional HR | LMS | Comms |
| --- | --- | --- | --- | --- | --- | --- |
| Charter | A | R | C | C | I | I |
| Curriculum | I | C | A/R | C | I | I |
| Localization | I | C | C | A/R | I | I |
| LMS | I | C | C | C | A/R | I |
| Scheduling | I | A/R | C | R | C | I |
| Communications | I | C | C | C | I | A/R |
| Reporting | I | A/R | C | C | C | I |

# 8. Schedule & Milestones

| Milestone | Baseline | Actual | Variance |
| --- | --- | --- | --- |
| Program Charter Approved | Apr 8, 2026 | Apr 8, 2026 | 0 days |
| Curriculum Baseline | Apr 17, 2026 | Apr 17, 2026 | 0 days |
| Localization Complete | Apr 24, 2026 | Apr 25, 2026 | +1 day |
| LMS & Enrollment Ready | Apr 29, 2026 | Apr 28, 2026 | -1 day |
| Regional Delivery Complete | Jun 5, 2026 | Jun 5, 2026 | 0 days |
| Executive Closeout | Jun 12, 2026 | Jun 12, 2026 | 0 days |

# 9. Risk & Issue Management

| ID | Item | Score | Mitigation / Resolution | Final Status |
| --- | --- | --- | --- | --- |
| R-01 | Time-zone conflicts may reduce attendance | 12 | Multiple session windows + recordings | Closed |
| R-02 | Localization delays may affect launch dates | 15 | Parallel review + priority content list | Closed |
| R-03 | Facilitator availability may create gaps | 12 | Backup facilitator pool | Closed |
| I-01 | LMS rules omitted a manager population | 20 | Corrected rule logic + participant reconciliation | Closed |
| D-01 | Regional sign-off required before communications | 16 | Approval tracking in governance meeting | Complete |

# 10. Budget Management

| Category | Baseline | Actual | Variance |
| --- | --- | --- | --- |
| Curriculum Design | $28,000 | $27,200 | +$800 |
| Localization & Translation | $22,000 | $23,150 | -$1,150 |
| LMS Configuration | $14,000 | $13,750 | +$250 |
| Facilitation & Delivery | $42,000 | $40,800 | +$1,200 |
| Communications & Materials | $12,000 | $11,600 | +$400 |
| Evaluation & Reporting | $10,000 | $9,800 | +$200 |
| TOTAL | $128,000 | $126,300 | +$1,700 favorable |

# 11. Communications Plan

| Audience | Purpose | Channel | Cadence | Owner |
| --- | --- | --- | --- | --- |
| Executive Sponsor | Health, risks, budget, decisions | Executive update | Biweekly | Project Coordinator |
| Working Team | Tasks, dependencies, RAID, changes | Working session | Weekly | Project Coordinator |
| Regional HR | Readiness, schedules, attendance | Regional sync | Weekly during rollout | Project Coordinator |
| Managers | Program expectations and reinforcement | Manager toolkit / email | Before cohorts | HR Communications |
| Participants | Access, schedule, reminders | Email + LMS | Per cohort | HR Communications |

# 12. Change Control

Changes are documented with reason, impact, owner, decision, and implementation status. Approved changes are incorporated into schedule, budget, communications, or delivery artifacts before execution.

# 13. Quality & Acceptance

Quality checks include curriculum approval, localization review, enrollment reconciliation, facilitator readiness, attendance reconciliation, completion validation, satisfaction review, and executive acceptance of the closeout report.

# 14. Lessons Learned

Time-zone planning should be completed before participant communications.

Localization review works best when priority content is identified early.

Backup facilitator coverage reduces delivery risk without changing the baseline schedule.

Automated LMS enrollment requires reconciliation against the authoritative participant list.

A single Excel dashboard improves consistency between weekly and executive reporting.