## Slide 1
Hospital Intake Workflow Optimization
Executive Project Update | Simulated Portfolio Case Study

## Slide 2
Executive Dashboard
Operational improvement and project controls at closeout
7.6 min
Registration
17.2 min
Wait Time
94%
Digital Adoption
1.8%
Data Error
4.6/5
Satisfaction
48.6%
Registration Reduction
44.5%
Wait Reduction
100%
Milestones
0
Open Issues
Simulated portfolio case study | No real patient data or PHI

## Slide 3
As-Is vs. To-Be Workflow
AS-IS
Paper / duplicate forms
TO-BE
Digital pre-registration
AS-IS
Insurance verification after arrival
TO-BE
Pre-arrival eligibility queue
AS-IS
Repeated demographic entry
TO-BE
Verified demographic prepopulation
AS-IS
Late missing-field discovery
TO-BE
Real-time validation
AS-IS
Inconsistent clinical handoff
TO-BE
Standard readiness checklist
Simulated portfolio case study | No real patient data or PHI

## Slide 4
Registration & Wait-Time Improvement
Chart: 
| W1 | W2 | W3 | W4 | W5 | W6
Registration Min | 14.8 | 13.2 | 11.6 | 10.1 | 8.9 | 7.6
Wait Min | 31 | 28.5 | 25 | 22.3 | 19.8 | 17.2
-48.6%
Registration
-44.5%
Wait Time
Simulated portfolio case study | No real patient data or PHI

## Slide 5
Adoption, Quality & Experience
Chart: 
| W1 | W2 | W3 | W4 | W5 | W6
Digital Form % | 42 | 55 | 68 | 79 | 88 | 94
Data Error % | 8.7 | 7.1 | 5.6 | 4.1 | 2.9 | 1.8
94%
Digital Adoption
1.8%
Data Error
4.6 / 5
Satisfaction
Simulated portfolio case study | No real patient data or PHI

## Slide 6
Milestone Performance
Charter Approved
On time
As-Is Mapping
On time
To-Be Design
1 day late
Pilot Ready
1 day early
Pilot Exit
On time
Full Rollout
On time
Closeout
On time
100%
Milestones
Simulated portfolio case study | No real patient data or PHI

## Slide 7
RAID & Defect Management
I-01 | Score 20 | Closed
Duplicate guarantor mapping defect
D-01 | Score 20 | Complete
Clinical leadership approval
R-02 | Score 15 | Closed
Eligibility backlog risk
R-01 | Score 12 | Closed
Emergency digital adoption risk
R-03 | Score 12 | Closed
Department practice variation risk
Simulated portfolio case study | No real patient data or PHI

## Slide 8
Budget Performance
Chart: 
| Analysis | Digital Intake | Eligibility | Training | Pilot/QA | Rollout
Baseline | 18000 | 26000 | 15000 | 16000 | 12000 | 18000
Actual | 17400 | 27150 | 14400 | 15350 | 11800 | 17050
$105K
Baseline
$103.15K
Actual
$1.85K
Favorable
Simulated portfolio case study | No real patient data or PHI

## Slide 9
Change Control & Lessons Learned
Approved Changes
Assisted digital intake station in Emergency Intake
Guarantor-field validation rule
Two-day pilot observation extension
Lessons Learned
Define eligibility queue ownership before shifting work upstream
Use real-time validation to prevent downstream rework
Pair defect severity with operational adoption in pilot exit criteria
Provide department-specific adoption support where needed
Simulated portfolio case study | No real patient data or PHI

## Slide 10
Closeout Summary
Simulated project objectives were met
-48.6%
Registration
-44.5%
Wait Time
94%
Digital Adoption
+1.8%
Budget
Project Coordinator contribution
Coordinated process mapping, pilot, rollout, stakeholders, RAID, and changes.
Built formula-driven Excel operational reporting and executive visibility.
Tracked workflow efficiency, adoption, quality, satisfaction, milestones, and budget through closeout.
Simulated portfolio case study | No real patient data or PHI