## Slide 1
Salesforce CRM Implementation
Executive Project Update | Simulated Portfolio Case Study

## Slide 2
Executive Dashboard
Implementation closed Green across schedule, quality, adoption, and budget
60
Requirements
72
Config Items
99.4%
Migration
98.2%
UAT Pass
98.6%
Adoption
98%
Training
100%
Milestones
+1.1%
Budget Variance
0
Open Defects
Simulated portfolio case study | Salesforce CRM Implementation

## Slide 3
Implementation Scope & Workstreams
Requirements
Stakeholder interviews, process needs, acceptance criteria
Salesforce Configuration
Sales Cloud objects, fields, flows, profiles, reporting
Data Migration
Legacy profiling, cleansing, mapping, mock loads, reconciliation
Integrations
Email/calendar and marketing handoffs
Testing
SIT, UAT, defects, permissions, regression
Enablement
Role-based training, champions, office hours, adoption reporting
Cutover & Hypercare
Production checklist, go-live, support, stabilization
Simulated portfolio case study | Salesforce CRM Implementation

## Slide 4
Data Migration Quality
Final migration exceeded the simulated 99% success target
Chart: 
| Accounts | Contacts | Leads | Opportunities
Success % | 99.5 | 99.4 | 99.3 | 99.6
14,850
Records Loaded
99.4%
Final Success
0
Open Migration Issues
Simulated portfolio case study | Salesforce CRM Implementation

## Slide 5
UAT & Defect Readiness
Chart: 
| W2 | W3 | W4 | W5 | W6
UAT Pass % | 78 | 86 | 92 | 96 | 98.2
228
Cases Executed
98.2%
Pass Rate
0
Open Defects
Simulated portfolio case study | Salesforce CRM Implementation

## Slide 6
Training & User Adoption
Chart: 
| W1 | W2 | W3 | W4 | W5 | W6
Login Adoption % | 0 | 18 | 49 | 72 | 91 | 98.6
98%
Training
138
Active Users
98.6%
Login Adoption
Simulated portfolio case study | Salesforce CRM Implementation

## Slide 7
Milestones & RAID
All implementation milestones completed; no open RAID items at closeout
Charter
On time
Requirements
On time
Solution Design
1 day late
Build
On time
UAT Sign-Off
On time
Go-Live
On time
Hypercare Exit
On time
100%
Milestones
0
Open RAID
Simulated portfolio case study | Salesforce CRM Implementation

## Slide 8
Budget Performance
Chart: 
| Discovery | Config | Migration | Integration | Testing | Training | Cutover
Baseline | 22000 | 36000 | 24000 | 18000 | 16000 | 14000 | 20000
Actual | 21400 | 35450 | 25800 | 17600 | 15450 | 13600 | 19100
$150K
Baseline
$148.4K
Actual
$1.6K
Favorable
Simulated portfolio case study | Salesforce CRM Implementation

## Slide 9
Change Control & Lessons Learned
Approved Changes
Lead-source normalization rules
Manager pipeline-hygiene dashboard
Extended hypercare office hours
Lessons Learned
Start data profiling during discovery
Pair technical migration success with business reconciliation
Include negative-access tests for permissions
Track adoption after training, not just attendance
Simulated portfolio case study | Salesforce CRM Implementation

## Slide 10
Closeout Summary
Simulated implementation objectives were met
99.4%
Migration
98.2%
UAT
98.6%
Adoption
+1.1%
Budget
Project Coordinator contribution
Coordinated requirements, build, migration, UAT, training, cutover, and hypercare.
Maintained RAID, milestones, budget, changes, actions, and executive reporting.
Built formula-driven Excel reporting for migration quality, UAT, defects, and adoption.
Simulated portfolio case study | Salesforce CRM Implementation