# Salesforce CRM Implementation

Project Charter & Management Plan | Simulated Portfolio Case Study

Portfolio disclosure: This is a simulated Salesforce implementation created to demonstrate project-coordination practices.

# 1. Executive Summary

This project coordinates a simulated Salesforce CRM implementation for Sales, Marketing, and Operations. The Project Coordinator manages governance, requirements, configuration tracking, data migration, integrations, testing, user training, cutover, hypercare, risk management, budget monitoring, and executive reporting.

# 2. Business Need

The organization is replacing fragmented legacy CRM processes with Salesforce to improve customer-data visibility, standardize lead and opportunity management, strengthen reporting, and provide a shared system of record across revenue teams.

# 3. Objectives

Approve 60 prioritized requirements; complete 72 configuration items; migrate legacy CRM data with at least 99% final success; achieve at least 97% UAT pass rate; complete at least 95% of training; reach at least 95% login adoption; close all critical defects before hypercare exit; complete all milestones; and remain within the $150,000 baseline budget.

# 4. Scope

In scope: discovery, requirements, solution design, Sales Cloud configuration, profiles and permissions, legacy data migration, email/calendar and marketing handoffs, SIT, UAT, training, cutover, hypercare, adoption reporting, and closeout. Out of scope: custom Salesforce product development, CPQ implementation, ERP replacement, and production customer data.

# 5. Success Measures

| Metric | Target | Simulated Result | Status |
| --- | --- | --- | --- |
| Requirements approved | 60 | 60 | Met |
| Configuration items | 72 | 72 | Met |
| Final migration success | >=99% | 99.4% | Met |
| UAT pass rate | >=97% | 98.2% | Met |
| Training completion | >=95% | 98% | Met |
| Login adoption | >=95% | 98.6% | Met |
| Open defects at hypercare exit | 0 | 0 | Met |
| Budget | <=$150,000 | $148,400 | Met |

# 6. Workstreams & Deliverables

| Workstream | Deliverables | Primary Owner |
| --- | --- | --- |
| Governance | Charter, status cadence, RAID, change log, closeout | Project Coordinator |
| Requirements | Stakeholder interviews, requirements backlog, acceptance criteria | Business Analyst |
| Solution Design | Objects, fields, automation, security model | Solution Architect |
| Configuration | Sales Cloud setup, reports, dashboards, flows | Salesforce Admin |
| Data Migration | Profiling, mapping, cleansing, mock loads, reconciliation | Data Lead |
| Integration | Email/calendar and marketing system handoffs | Integration Lead |
| Testing | SIT, UAT, defect triage, regression | QA Lead / Project Coordinator |
| Training & Adoption | Role-based training, champions, office hours, adoption KPIs | Change Lead |
| Cutover & Hypercare | Cutover checklist, go-live, support, stabilization | Project Coordinator |

# 7. Governance & RACI

Weekly implementation meetings review workstream progress, dependencies, RAID, defects, and changes. During UAT and cutover, defect/cutover huddles increase in frequency. Executive updates are delivered biweekly.

| Activity | Sponsor | Project Coord. | BA | SF Admin | Data | QA | Change |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Charter | A | R | C | I | I | I | I |
| Requirements | I | C | A/R | C | C | I | I |
| Solution Design | I | C | C | A/R | C | C | I |
| Configuration | I | C | C | A/R | I | C | I |
| Migration | I | C | C | C | A/R | C | I |
| UAT | I | A/R | C | C | C | R | I |
| Training | I | C | C | C | I | I | A/R |
| Cutover | I | A/R | C | R | R | R | R |

# 8. Schedule & Milestones

| Milestone | Baseline | Actual | Variance |
| --- | --- | --- | --- |
| Charter Approved | Jan 7, 2026 | Jan 7, 2026 | 0 days |
| Requirements Baseline | Jan 16, 2026 | Jan 16, 2026 | 0 days |
| Solution Design Approved | Jan 23, 2026 | Jan 24, 2026 | +1 day |
| Build Complete | Feb 12, 2026 | Feb 12, 2026 | 0 days |
| UAT Sign-Off | Mar 6, 2026 | Mar 6, 2026 | 0 days |
| Production Go-Live | Mar 20, 2026 | Mar 20, 2026 | 0 days |
| Hypercare Exit | Apr 3, 2026 | Apr 3, 2026 | 0 days |

# 9. Data Migration Plan

| Object | Source Records | Loaded | Final Success | Control |
| --- | --- | --- | --- | --- |
| Accounts | 3,200 | 3,184 | 99.5% | Reconcile counts and required fields |
| Contacts | 6,900 | 6,858 | 99.4% | Deduplication and matching rules |
| Leads | 3,100 | 3,078 | 99.3% | Lead-source normalization |
| Opportunities | 1,650 | 1,643 | 99.6% | Owner/stage validation |

# 10. Testing & Acceptance

Testing includes system integration testing, 228 business UAT cases, defect triage by severity, regression testing, security/permission validation, and formal UAT sign-off. Production cutover requires zero open critical defects and accepted migration reconciliation.

# 11. Risk & Issue Management

| ID | Item | Score | Mitigation / Resolution | Status |
| --- | --- | --- | --- | --- |
| R-01 | Legacy data quality may reduce migration accuracy | 15 | Profile, cleanse, dedupe, two mock migrations | Closed |
| R-02 | User adoption may lag after go-live | 12 | Training, champions, office hours, adoption dashboard | Closed |
| R-03 | Permission model may expose records incorrectly | 10 | Role hierarchy review + negative access tests | Closed |
| I-01 | Initial mock migration produced duplicate contacts | 20 | Adjusted matching rules and reran load | Closed |
| D-01 | Business UAT sign-off required before cutover | 20 | Daily UAT triage and formal sign-off checklist | Complete |

# 12. Budget Management

| Category | Baseline | Actual | Variance |
| --- | --- | --- | --- |
| Discovery & Design | $22,000 | $21,400 | +$600 |
| Salesforce Configuration | $36,000 | $35,450 | +$550 |
| Data Migration | $24,000 | $25,800 | -$1,800 |
| Integrations | $18,000 | $17,600 | +$400 |
| Testing & UAT | $16,000 | $15,450 | +$550 |
| Training & Change | $14,000 | $13,600 | +$400 |
| Cutover & Hypercare | $20,000 | $19,100 | +$900 |
| TOTAL | $150,000 | $148,400 | +$1,600 favorable |

# 13. Change Control

Changes are documented with business reason, impact, decision, owner, and implementation status. Approved changes are incorporated into configuration, data rules, adoption support, or the cutover plan.

# 14. Lessons Learned

Data profiling should begin during requirements, not after configuration starts.

Mock migrations need business reconciliation criteria in addition to technical load success.

Permission testing should include negative-access scenarios before UAT sign-off.

Training completion alone is not enough; adoption dashboards should track actual user activity after launch.

Cutover readiness is easier to govern when defects, migration, training, and approvals roll into one executive dashboard.