## Weekly Metrics
Week | Requirements Approved | Config Items Complete | Migration Records Loaded | Migration Success % | UAT Cases Executed | UAT Pass % | Critical Defects | Open Defects | Training Completion % | Active Users | Login Adoption % | Milestones Completed
Week 1 | 18 | 12 | 0 |  | 0 |  | 4 | 18 | 0% | 0 | 0% | 1
Week 2 | 34 | 28 | 2500 | 91% | 45 | 78% | 3 | 16 | 22% | 25 | 18% | 1
Week 3 | 47 | 43 | 7200 | 95% | 96 | 86% | 2 | 11 | 48% | 68 | 49% | 1
Week 4 | 56 | 57 | 11800 | 97% | 154 | 92% | 1 | 6 | 71% | 101 | 72% | 1
Week 5 | 60 | 68 | 14500 | 98.5% | 210 | 96% | 0 | 3 | 91% | 128 | 91% | 1
Week 6 | 60 | 72 | 14850 | 99.4% | 228 | 98.2% | 0 | 0 | 98% | 138 | 98.6% | 1

## Workstream Status
Workstream | Owner | Baseline % | Current % | Variance | Status | Key Deliverable | Open Items | Dependency | Notes
Requirements | Business Analyst | 100% | 100% | 0% | Complete | Approved requirements backlog | 0 | None | 60 requirements approved
Salesforce Configuration | Salesforce Admin | 100% | 100% | 0% | Complete | Configured objects, fields, flows, profiles | 0 | Requirements | 72 config items completed
Data Migration | Data Lead | 100% | 99.4% | -0.6% | Complete | Validated legacy CRM migration | 0 | Configuration | 14,850 records loaded
Integration | Integration Lead | 100% | 100% | 0% | Complete | Email/calendar + marketing handoff | 0 | Configuration | Interfaces validated
UAT | QA Lead | 100% | 98.2% | -1.8% | Complete | Business UAT and sign-off | 0 | Config + Migration | 228 cases executed
Training & Adoption | Change Lead | 100% | 98% | -2% | Complete | Role-based training + adoption support | 0 | UAT | 98% training completion
Cutover & Hypercare | Project Coordinator | 100% | 100% | 0% | Complete | Production cutover and stabilization | 0 | All workstreams | No open Sev-1/2 defects

## Task Tracker
ID | Workstream | Task | Owner | Priority | Status | Start Date | Due Date | % Complete | Dependency | Days to Due | Health | Sprint / Phase | Notes
SF-001 | Governance | Approve implementation charter | Project Coordinator | High | Complete | 2026-01-05 | 2026-01-07 | 100% | None | 0 | Green | Initiation | Sponsor approved
SF-002 | Requirements | Complete stakeholder interviews and requirements backlog | Business Analyst | Critical | Complete | 2026-01-06 | 2026-01-16 | 100% | SF-001 | 0 | Green | Discovery | 60 requirements baselined
SF-003 | Design | Approve solution design and data model | Solution Architect | Critical | Complete | 2026-01-14 | 2026-01-23 | 100% | SF-002 | 0 | Green | Design | Objects, fields, permissions approved
SF-004 | Configuration | Configure core Sales Cloud workflow | Salesforce Admin | Critical | Complete | 2026-01-20 | 2026-02-06 | 100% | SF-003 | 0 | Green | Build | Lead, account, contact, opportunity workflow
SF-005 | Data Migration | Cleanse and map legacy CRM data | Data Lead | Critical | Complete | 2026-01-20 | 2026-02-10 | 100% | SF-003 | 0 | Green | Build | Mapping and dedupe rules approved
SF-006 | Integration | Configure email/calendar and marketing handoff | Integration Lead | High | Complete | 2026-01-27 | 2026-02-12 | 100% | SF-003 | 0 | Green | Build | Interfaces validated
SF-007 | Migration | Execute mock migration #1 | Data Lead | Critical | Complete | 2026-02-05 | 2026-02-11 | 100% | SF-005 | 0 | Green | Test | 91% initial success
SF-008 | QA | Execute system integration testing | QA Lead | Critical | Complete | 2026-02-09 | 2026-02-20 | 100% | SF-004, SF-006 | 0 | Green | Test | Critical defects triaged
SF-009 | UAT | Coordinate user acceptance testing | Project Coordinator | Critical | Complete | 2026-02-23 | 2026-03-06 | 100% | SF-004, SF-007, SF-008 | 0 | Green | UAT | 228 cases executed
SF-010 | Training | Deliver role-based user training | Change Lead | High | Complete | 2026-03-02 | 2026-03-13 | 100% | SF-009 | 0 | Green | Enablement | 98% training completion
SF-011 | Cutover | Execute production cutover | Project Coordinator | Critical | Complete | 2026-03-16 | 2026-03-20 | 100% | SF-009, SF-010 | 0 | Green | Go-Live | Cutover checklist complete
SF-012 | Hypercare | Monitor adoption, defects, and support | Project Coordinator | High | Complete | 2026-03-23 | 2026-04-03 | 100% | SF-011 | 0 | Green | Hypercare | No open Sev-1/2 defects
Formulas:
Days to Due = IF([Status]="Complete",0,[Due Date]-TODAY())
Health = IF([Status]="Complete","Green",IF([Due Date]<TODAY(),"Red",IF([Due Date]-TODAY()<=3,"Amber","Green")))

## Data Migration
Object | Source Records | Loaded | Rejected | Success % | Duplicate Rate % | Required Field Pass % | Owner | Mock 1 | Mock 2 | Final | Status
Accounts | 3200 | 3184 | 16 | 99.5% | 1.2% | 99.6% | Data Lead | 94% | 98% | 99.5% | Complete
Contacts | 6900 | 6858 | 42 | 99.39% | 1.8% | 99.2% | Data Lead | 90% | 97% | 99.4% | Complete
Leads | 3100 | 3078 | 22 | 99.29% | 2.1% | 98.9% | Data Lead | 89% | 96% | 99.3% | Complete
Opportunities | 1650 | 1643 | 7 | 99.58% | 0.5% | 99.8% | Data Lead | 93% | 99% | 99.6% | Complete

## UAT & Defects
Area | Cases Planned | Cases Executed | Passed | Failed | Pass % | Critical Defects | High Defects | Medium/Low | Retest Complete % | Status
Lead Management | 40 | 40 | 40 | 0 | 100% | 0 | 0 | 2 | 100% | Complete
Account / Contact | 44 | 44 | 43 | 1 | 97.73% | 0 | 1 | 2 | 100% | Complete
Opportunity Management | 52 | 52 | 51 | 1 | 98.08% | 0 | 1 | 3 | 100% | Complete
Activities / Email | 32 | 32 | 32 | 0 | 100% | 0 | 0 | 1 | 100% | Complete
Reports / Dashboards | 28 | 28 | 27 | 1 | 96.43% | 0 | 1 | 2 | 100% | Complete
Permissions / Roles | 32 | 32 | 31 | 1 | 96.88% | 0 | 1 | 1 | 100% | Complete

## Training & Adoption
Role | Target Users | Trained | Training % | Active Users | Login Adoption % | Tasks Completed in CRM % | Avg Support Tickets/User | Satisfaction | Status
Sales Reps | 95 | 94 | 98.95% | 9300% | 97.89% | 96% | 0.08 | 4.6 | Adopted
Sales Managers | 18 | 18 | 100% | 1800% | 100% | 98% | 0.05 | 4.7 | Adopted
Marketing | 15 | 15 | 100% | 1500% | 100% | 93% | 0.09 | 4.5 | Adopted
Operations | 12 | 11 | 91.67% | 1200% | 100% | 95% | 0.07 | 4.6 | Adopted

## RAID Log
RAID ID | Type | Description | Impact | Probability | Score | Owner | Response / Mitigation | Target Date | Status | Escalation | Days to Target | Risk Level
R-01 | Risk | Legacy CRM data quality may reduce migration accuracy | 5 | 3 | 15 | Data Lead | Profile, cleanse, dedupe, and execute two mock migrations | 2026-03-10 | Closed | Yes | 0 | Critical
R-02 | Risk | User adoption may lag after go-live | 4 | 3 | 12 | Change Lead | Role-based training, champions, office hours, adoption dashboard | 2026-03-31 | Closed | No | 0 | High
R-03 | Risk | Permission model may expose records incorrectly | 5 | 2 | 10 | Solution Architect | Role hierarchy review and negative-access test cases | 2026-03-06 | Closed | Yes | 0 | High
I-01 | Issue | Initial migration produced duplicate contacts | 5 | 4 | 20 | Data Lead | Adjust matching rules, cleanse source, rerun mock migration | 2026-02-18 | Closed | Yes | 0 | Critical
D-01 | Dependency | Business UAT sign-off required before cutover | 5 | 4 | 20 | Project Coordinator | Daily UAT triage and formal sign-off checklist | 2026-03-06 | Complete | Yes | 0 | Critical
Formulas:
Days to Target = IF(OR([Status]="Closed",[Status]="Complete",[Status]="Validated"),0,[Target Date]-TODAY())

## Milestones
Milestone | Baseline Date | Actual Date | Status | Days Variance | Exit Criteria | Owner | On-Time? | Schedule Performance
Charter Approved | 2026-01-07 | 2026-01-07 | Complete | 0 | Sponsor approval | Project Coordinator | Yes | On/Ahead
Requirements Baseline | 2026-01-16 | 2026-01-16 | Complete | 0 | Requirements signed off | Business Analyst | Yes | On/Ahead
Solution Design Approved | 2026-01-23 | 2026-01-24 | Complete | 1 | Architecture and data model approved | Solution Architect | No | Minor Delay
Build Complete | 2026-02-12 | 2026-02-12 | Complete | 0 | Configuration and integrations complete | Salesforce Admin | Yes | On/Ahead
UAT Sign-Off | 2026-03-06 | 2026-03-06 | Complete | 0 | Business approval | Project Coordinator | Yes | On/Ahead
Production Go-Live | 2026-03-20 | 2026-03-20 | Complete | 0 | Cutover validated | Project Coordinator | Yes | On/Ahead
Hypercare Exit | 2026-04-03 | 2026-04-03 | Complete | 0 | No Sev-1/2 open defects | Project Coordinator | Yes | On/Ahead

## Budget
Category | Baseline Budget | Actual Cost | Variance | Variance % | Forecast at Completion | Notes
Discovery & Design | 22000 | 21400 | 600 | 2.727% | 21400 | Within plan
Salesforce Configuration | 36000 | 35450 | 550 | 1.528% | 35450 | Below baseline
Data Migration | 24000 | 25800 | -1800 | -7.5% | 25800 | Extra cleansing and rerun effort
Integrations | 18000 | 17600 | 400 | 2.222% | 17600 | Within plan
Testing & UAT | 16000 | 15450 | 550 | 3.438% | 15450 | Below baseline
Training & Change | 14000 | 13600 | 400 | 2.857% | 13600 | Digital training reduced cost
Cutover & Hypercare | 20000 | 19100 | 900 | 4.5% | 19100 | Lower support overtime
Summary | Baseline | Actual / Forecast | Variance | Variance % | Forecast
Total | 150000 | 148400 | 1600 | 1.067% | 148400
Contingency | 12000 | 13600

## RACI & Stakeholders
Activity | Executive Sponsor | Project Coordinator | Business Analyst | Salesforce Admin | Data Lead | QA Lead | Change Lead | Sales Leadership
Charter | A | R | C | I | I | I | I | C
Requirements | I | C | A/R | C | C | I | I | R
Solution Design | I | C | C | A/R | C | C | I | C
Configuration | I | C | C | A/R | I | C | I | C
Data Migration | I | C | C | C | A/R | C | I | I
UAT | I | A/R | C | C | C | R | I | R
Training | I | C | C | C | I | I | A/R | R
Cutover | I | A/R | C | R | R | R | R | C
Hypercare | I | A/R | C | R | C | R | R | C
Stakeholder | Role | Influence | Interest | Communication | Cadence | Owner | Key Need
Executive Sponsor | Sales / Operations sponsor | High | High | Executive update | Biweekly | Project Coordinator | Health, risks, budget, adoption
Sales Leadership | Primary business owner | High | High | Working session | Weekly | Project Coordinator | Pipeline workflow and adoption
Sales Operations | Process owner | High | High | Requirements / UAT sync | Weekly | Project Coordinator | Data quality, reporting, workflow
IT / Salesforce Admin | Technical delivery | High | High | Build / defect triage | 2x weekly during build | Project Coordinator | Configuration, security, defects
End Users | Sales / marketing / operations users | Medium | High | Training / office hours | Per rollout plan | Change Lead | Usability, training, support

## Change Log
Change ID | Request | Reason | Impact | Decision | Decision Date | Owner | Status
CR-01 | Add lead-source normalization rules | Improve reporting consistency across migrated records | Adds cleansing logic; no go-live impact | Approved | 2026-02-03 | Data Lead | Implemented
CR-02 | Add manager dashboard for pipeline hygiene | Sales leadership requested visibility into stale opportunities | Minor configuration effort; no schedule impact | Approved | 2026-02-20 | Salesforce Admin | Implemented
CR-03 | Extend hypercare office hours by one week | Support adoption after launch | Small support-cost increase within contingency | Approved | 2026-03-23 | Change Lead | Implemented

## Dashboard
Salesforce CRM Implementation ¦ Executive Dashboard
[5 empty] | Week | UAT Pass % | Week | Login Adoption % | Object | Migration Success %
[5 empty] | W1 | 0% | W1 | 0% | Accounts | 99.5%
Implementation KPI | Value | Project Health | Value |  | W2 | 78% | W2 | 18% | Contacts | 99.39%
Overall Status | Green | Open Risks / Issues | 0 |  | W3 | 86% | W3 | 49% | Leads | 99.29%
Requirements Approved | 60 | Open Critical RAID Items | 0 |  | W4 | 92% | W4 | 72% | Opportunities | 99.58%
Config Completion | 100% | Milestone Completion | 100% |  | W5 | 96% | W5 | 91%
Migration Success | 99.4% | Budget Variance | 1.067% |  | W6 | 98.2% | W6 | 98.6%
UAT Pass Rate | 98.2% | Task Completion | 100%
Training Completion | 98% | Open Defects | 0
Login Adoption | 98.6% | Hypercare Status | Stable
Executive Summary
Scope | Simulated Salesforce CRM implementation for sales, marketing, and operations, including configuration, migration, integrations, UAT, training, cutover, and hypercare.
Data Migration | 14,850 legacy CRM records loaded with 99.4% final migration success.
Quality | UAT reached 98.2% pass rate with zero open defects at hypercare exit.
Adoption | 98% training completion and 98.6% login adoption across 140 targeted users.
Delivery | All milestones and implementation tasks completed with zero open RAID items.
Budget | Actual implementation cost finished below the $150,000 baseline budget.
Project Controls Demonstrated
Implementation Delivery |  | Governance & Risk |  | CRM Analytics & Adoption
Requirements / design Configuration & integration Migration & UAT Cutover / hypercare |  | RAID scoring RACI / stakeholders Change control Milestones / budget |  | Migration quality UAT pass rate Training completion Login adoption

## Formula Guide
Area | Formula Example | Purpose | Interview Talking Point
Data Migration | =IFERROR(C2/B2,0) | Calculates load success rate | Shows migration quality by Salesforce object.
UAT & Defects | =IFERROR(D2/C2,0) | Calculates UAT pass rate | Tracks readiness for production cutover.
Training & Adoption | =IFERROR(C2/B2,0) | Calculates training completion | Measures enablement readiness.
Task Tracker | -46291 | Days remaining | Supports proactive implementation schedule management.
RAID Log | =D2*E2 | Risk score | Standardizes implementation risk prioritization.
Milestones | =C2-B2 | Schedule variance | Compares actual milestone dates to baseline.
Budget | =B2-C2 | Cost variance | Tracks implementation budget performance.
Dashboard | =COUNTIF('Task Tracker'!F2:F13,"Complete")/COUNTA('Task Tracker'!A2:A13) | Task completion KPI | Links executive dashboard directly to delivery tracker.