## Weekly Metrics
Week | Tasks Planned | Tasks Completed | Open Issues | Closed Issues | Team Velocity | Milestones Due | Milestones Completed | Completion % | Issue Closure % | Milestone Completion %
Week 1 | 14 | 12 | 2 | 1 | 24 | 2 | 2 | 85.71% | 33.33% | 100%
Week 2 | 17 | 15 | 3 | 2 | 30 | 2 | 1 | 88.24% | 40% | 50%
Week 3 | 19 | 18 | 1 | 4 | 36 | 2 | 2 | 94.74% | 80% | 100%
Week 4 | 20 | 19 | 1 | 2 | 38 | 2 | 2 | 95% | 66.67% | 100%
Week 5 | 22 | 21 | 0 | 2 | 42 | 1 | 1 | 95.45% | 100% | 100%
Week 6 | 24 | 24 | 0 | 1 | 48 | 1 | 1 | 100% | 100% | 100%

## Task Tracker
ID | Workstream | Task | Owner | Priority | Status | Start Date | Due Date | % Complete | Dependency | Days to Due | Health | Schedule % Used
EC-001 | Project Mgmt | Approve project charter | Project Coordinator | High | Complete | 2026-07-06 | 2026-07-08 | 100% | None | 0 | Green | 100%
EC-002 | Platform | Configure storefront framework | Engineering Lead | High | Complete | 2026-07-08 | 2026-07-17 | 100% | EC-001 | 0 | Green | 100%
EC-003 | Catalog | Load initial product catalog | Product Lead | High | Complete | 2026-07-13 | 2026-07-24 | 100% | EC-002 | 0 | Green | 100%
EC-004 | Payments | Integrate payment gateway | Engineering Lead | Critical | Complete | 2026-07-13 | 2026-07-27 | 100% | EC-002 | 0 | Green | 100%
EC-005 | QA | Execute checkout test cases | QA Lead | Critical | Complete | 2026-07-27 | 2026-08-05 | 100% | EC-003, EC-004 | 0 | Green | 100%
EC-006 | Security | Complete security review | Security Analyst | Critical | Complete | 2026-07-29 | 2026-08-07 | 100% | EC-004 | 0 | Green | 100%
EC-007 | Operations | Finalize support runbook | Operations Lead | Medium | Complete | 2026-08-03 | 2026-08-12 | 100% | EC-005 | 0 | Green | 100%
EC-008 | Launch | Go-live readiness review | Project Coordinator | Critical | Complete | 2026-08-10 | 2026-08-14 | 100% | EC-005, EC-006, EC-007 | 0 | Green | 100%
EC-009 | Launch | Production deployment | Engineering Lead | Critical | Complete | 2026-08-17 | 2026-08-17 | 100% | EC-008 | 0 | Green | 0%
EC-010 | Post-Launch | Hypercare issue monitoring | Project Coordinator | High | Complete | 2026-08-18 | 2026-08-28 | 100% | EC-009 | 0 | Green | 100%
Formulas:
Days to Due = IF([Status]="Complete",0,[Due Date]-TODAY())
Health = IF([Status]="Complete","Green",IF([Due Date]<TODAY(),"Red",IF([Due Date]-TODAY()<=3,"Amber","Green")))
Schedule % Used = IFERROR((MIN(TODAY(),[Due Date])-[Start Date])/([Due Date]-[Start Date]),0)

## RAID Log
RAID ID | Type | Description | Impact | Probability | Score | Owner | Response / Mitigation | Target Date | Status | Escalation | Days to Target | Risk Level
R-01 | Risk | Payment gateway certification could delay launch | 5 | 3 | 15 | Engineering Lead | Complete certification in staging; maintain backup processor | 2026-08-07 | Closed | No | 0 | Critical
R-02 | Risk | Catalog data quality may create incorrect product listings | 4 | 3 | 12 | Product Lead | Run validation rules and sample audit before UAT | 2026-07-31 | Closed | No | 0 | High
I-01 | Issue | Three checkout defects found during UAT | 5 | 4 | 20 | QA Lead | Daily defect triage; critical defects fixed before readiness review | 2026-08-10 | Closed | Yes | 0 | Critical
A-01 | Assumption | Support team available for launch-week hypercare | 3 | 2 | 6 | Operations Lead | Confirm staffing one week before launch | 2026-08-10 | Validated | No | 0 | Medium
D-01 | Dependency | Security sign-off required before production deployment | 5 | 4 | 20 | Security Analyst | Reserve review window and track evidence package | 2026-08-07 | Complete | Yes | 0 | Critical
Formulas:
Days to Target = IF(OR([Status]="Closed",[Status]="Complete",[Status]="Validated"),0,[Target Date]-TODAY())

## Milestones
Milestone | Baseline Date | Actual Date | Status | Days Variance | Exit Criteria | Owner | On-Time? | Schedule Performance
Charter Approved | 2026-07-08 | 2026-07-08 | Complete | 0 | Sponsor approval received | Project Coordinator | Yes | On/Ahead
Storefront Build Complete | 2026-07-24 | 2026-07-23 | Complete | -1 | Core storefront features complete | Engineering Lead | Yes | On/Ahead
Payment Integration Complete | 2026-07-31 | 2026-08-01 | Complete | 1 | Successful sandbox transactions | Engineering Lead | No | Minor Delay
UAT Complete | 2026-08-07 | 2026-08-08 | Complete | 1 | Critical defects resolved | QA Lead | No | Minor Delay
Go-Live Readiness | 2026-08-14 | 2026-08-14 | Complete | 0 | All launch criteria approved | Project Coordinator | Yes | On/Ahead
Production Launch | 2026-08-17 | 2026-08-17 | Complete | 0 | Deployment validated | Engineering Lead | Yes | On/Ahead

## Budget
Category | Baseline Budget | Actual Cost | Variance | Variance % | Forecast at Completion | Notes
Platform Development | 42000 | 40500 | 1500 | 3.571% | 40500 | Completed below baseline
Payment Integration | 12000 | 12800 | -800 | -6.667% | 12800 | Certification support increased cost
QA & Testing | 16000 | 15750 | 250 | 1.562% | 15750 | Within plan
Security Review | 9000 | 9000 | 0 | 0% | 9000 | On budget
Launch & Hypercare | 11000 | 10400 | 600 | 5.455% | 10400 | Lower support overtime
Summary | Baseline | Actual / Forecast
Total | 90000 | 88450 | 1550 | 1.722% | 88450
Remaining Contingency | 5000 | 6550 | 1550

## RACI & Stakeholders
Deliverable / Decision | Sponsor | Project Coordinator | Engineering Lead | Product Lead | QA Lead | Security | Operations
Project Charter | A | R | C | C | I | I | I
Storefront Build | I | C | A/R | C | C | I | I
Catalog Readiness | I | C | C | A/R | C | I | I
Payment Integration | I | C | A/R | I | C | C | I
UAT Sign-off | I | C | C | C | A/R | C | I
Security Approval | I | C | C | I | C | A/R | I
Go-Live Decision | A | R | C | C | C | C | C
Hypercare | I | R | C | I | C | I | A
Stakeholder | Role | Influence | Interest | Engagement Strategy | Cadence
Executive Sponsor | Decision maker | High | High | Concise status, risks, decisions needed | Weekly
Engineering Lead | Delivery owner | High | High | Daily blockers and dependency review | Daily
Product Lead | Business readiness | High | High | Scope and acceptance alignment | 2x weekly
QA Lead | Quality owner | Medium | High | Defect and test progress review | Daily during UAT
Operations Lead | Support readiness | Medium | High | Runbook and hypercare readiness | Weekly

## Change Log
Change ID | Request | Reason | Impact | Decision | Decision Date | Owner
CR-01 | Add guest checkout | Reduce purchase friction | +3 dev days; no launch-date change | Approved | 2026-07-20 | Product Lead
CR-02 | Add second payment processor | Resilience improvement | Would add 2 weeks | Deferred | 2026-07-28 | Executive Sponsor
CR-03 | Expand launch catalog by 500 SKUs | Commercial request | Higher data-quality risk | Approved with phased upload | 2026-08-03 | Product Lead

## Dashboard
E-Commerce Platform Launch ¦ Executive Project Dashboard
KPI | Value | Delivery Health | Value | Week | Tasks Completed
Overall Status | Green | Open Risks / Issues | 0 | Week 1 | 12
Task Completion | 100% | Critical RAID Items | 3 | Week 2 | 15
Milestone Completion | 100% | Current Velocity | 48 | Week 3 | 18
Budget Variance | 1.722% | Launch Date | 2026-08-17 | Week 4 | 19
|  |  |  | Week 5 | 21
Executive Summary |  |  |  | Week 6 | 24
Scope | Launch a secure e-commerce storefront with catalog, payments, testing, deployment, and hypercare.
Schedule | Launch completed on baseline date; two interim milestones had 1-day variance.
Budget | Project completed below baseline budget after offsetting payment-integration overage. |  |  | Week | Velocity
Quality | UAT defects were triaged daily; all critical defects closed before readiness approval. |  |  | Week 1 | 24
Risk | Payment certification and catalog-quality risks were mitigated before production deployment. |  |  | Week 2 | 30
Outcome | 24/24 planned tasks completed in final week; velocity increased from 24 to 48 across six weeks. |  |  | Week 3 | 36
|  |  |  | Week 4 | 38
|  |  |  | Week 5 | 42
|  |  |  | Week 6 | 48
Dashboard Interpretation
This dashboard is built directly in Excel. KPI cards are formula-driven from the Task Tracker, RAID Log, Milestones, Budget, and Weekly Metrics sheets. Charts are native Excel charts and update when the underlying project data changes.

## Formula Guide
Area | Formula Example | Purpose | Interview Talking Point
Weekly Metrics | =IFERROR(C2/B2,0) | Weekly task completion rate | Automates KPI tracking.
Task Tracker | =IF(F2="Complete",0,H2-TODAY()) | Days remaining | Supports proactive deadline monitoring.
Task Tracker | =IF(F2="Complete","Green",IF(H2<TODAY(),"Red",IF(H2-TODAY()<=3,"Amber","Green"))) | RAG health | Automatically flags schedule risk.
RAID Log | =D2*E2 | Risk score | Standardizes risk prioritization.
RAID Log | =IF(F2>=15,"Critical",IF(F2>=10,"High",IF(F2>=5,"Medium","Low"))) | Risk severity | Supports escalation decisions.
Milestones | =IF(C2="","",C2-B2) | Schedule variance | Compares actual vs baseline.
Budget | =B2-C2 | Cost variance | Shows favorable/unfavorable performance.
Budget | =IFERROR(D2/B2,0) | Variance % | Normalizes variance across categories.
Dashboard | =COUNTIF('Task Tracker'!F2:F11,"Complete")/COUNTA('Task Tracker'!A2:A11) | Dashboard completion KPI | Links dashboard to source tracker.
Dashboard | ='Weekly Metrics'!F7 | Current velocity | Synchronizes executive reporting.