Project Status Meeting Notes

Week 4 | E-Commerce Platform Launch

| Meeting | Date / Time | Facilitator |
| --- | --- | --- |
| Cross-Functional Status Review | August 6, 2026 ¦ 10:00-10:45 AM | Project Coordinator |

# Attendees

Project Coordinator, Engineering Lead, Product Lead, QA Lead, Security Analyst, Operations Lead

# Agenda

Review schedule and milestone health

Review UAT progress and defect status

Confirm payment certification and security dependency

Review launch-readiness actions

Capture decisions, owners, and due dates

# Discussion Summary

| Topic | Discussion / Outcome |
| --- | --- |
| Schedule | Overall launch remains on track for August 17. UAT completion is trending one day late but float remains. |
| Payments | Certification testing completed; one documentation item remains before closure. |
| UAT | Three checkout defects identified. One critical, two medium. Critical fix is in retest. |
| Security | Evidence package is 90% complete; final payment-control evidence due August 7. |
| Operations | Support runbook drafted; escalation contacts and monitoring thresholds require final confirmation. |

# Decisions

| Decision ID | Decision | Owner |
| --- | --- | --- |
| DEC-04 | Keep August 17 launch baseline; no schedule change | Executive Sponsor |
| DEC-05 | Critical checkout defect must pass retest before readiness gate | QA Lead |
| DEC-06 | Second payment processor remains deferred to post-launch backlog | Product Lead |

# Action Items

| Action | Owner | Due | Status |
| --- | --- | --- | --- |
| Complete critical checkout defect retest | QA Lead | Aug 7 | In Progress |
| Submit final security evidence | Engineering Lead | Aug 7 | In Progress |
| Confirm launch-week support roster | Operations Lead | Aug 10 | Not Started |
| Update executive status with UAT variance | Project Coordinator | Aug 6 | Complete |

# Next Meeting

Go-Live Readiness Review - August 14, 2026. Required pre-read: updated RAID log, UAT summary, security approval, deployment/rollback checklist, support roster.