E-Commerce Platform Launch

Integrated Project Charter & Management Plan | Project Coordinator Portfolio Case Study

# 1. Executive Summary

This simulated project coordinates the launch of a secure e-commerce platform across engineering, product catalog, payments, quality assurance, security, operations, and executive stakeholders. The project is structured as a six-week delivery effort with formal governance, measurable KPIs, controlled scope, risk management, launch readiness, and post-launch hypercare.

| Metric | Target / Baseline | Final Result |
| --- | --- | --- |
| Launch date | August 17, 2026 | Completed on baseline date |
| Budget | $90,000 + $5,000 contingency | $88,450 actual; 1.7% favorable variance |
| Final-week delivery | 24 planned tasks | 24 completed (100%) |
| Velocity | 24 baseline | 48 final week (+100%) |
| Open launch-blocking issues | 0 | 0 at go-live |

# 2. Business Need & Objectives

Create a production-ready digital storefront with catalog, checkout, payment, security, and support readiness.

Coordinate cross-functional workstreams and dependencies through a single source of truth.

Maintain transparent executive reporting for scope, schedule, budget, quality, risk, and decisions.

Complete launch readiness with all critical defects closed and required approvals documented.

Establish hypercare monitoring and lessons learned for transition to steady-state operations.

# 3. Scope Definition

| In Scope | Out of Scope |
| --- | --- |
| Storefront framework and responsive checkout | Native mobile application |
| Initial catalog configuration and validation | International market expansion |
| Payment gateway integration and certification | Second payment processor at initial launch |
| UAT, security review, deployment, hypercare | Long-term merchandising optimization |
| Project governance, status reporting, RAID, change control | Post-hypercare feature roadmap |

# 4. Governance & Roles

| Role | Primary Accountability | Decision / Escalation |
| --- | --- | --- |
| Executive Sponsor | Funding, strategic alignment, go-live approval | Scope/budget exceptions and go-live decision |
| Project Coordinator | Integrated plan, meetings, actions, RAID, reporting | Escalates blockers and decision needs |
| Engineering Lead | Build, integration, deployment | Technical feasibility and estimates |
| Product Lead | Catalog, requirements, acceptance | Business acceptance and scope detail |
| QA Lead | Test planning, defect triage, UAT | Quality exit criteria |
| Security Analyst | Security evidence and approval | Security sign-off |
| Operations Lead | Runbook, support readiness, hypercare | Operational acceptance |

# 5. Delivery Approach & Phase Gates

| Phase | Key Activities | Exit Criteria |
| --- | --- | --- |
| Initiate | Charter, stakeholders, scope, baseline | Charter approved |
| Plan | WBS, schedule, RACI, RAID, communications | Plan baselined |
| Build & Configure | Storefront, catalog, payments | Feature-complete staging build |
| Validate | UAT, security, defect triage | Critical defects closed; security approved |
| Launch | Readiness review, deployment, smoke test | Production validation complete |
| Hypercare & Close | Issue monitoring, transition, lessons learned | Support handoff accepted |

# 6. Milestone Schedule

| Milestone | Baseline | Actual | Variance |
| --- | --- | --- | --- |
| Charter Approved | Jul 8 | Jul 8 | 0 days |
| Storefront Build Complete | Jul 24 | Jul 23 | -1 day |
| Payment Integration Complete | Jul 31 | Aug 1 | +1 day |
| UAT Complete | Aug 7 | Aug 8 | +1 day |
| Go-Live Readiness | Aug 14 | Aug 14 | 0 days |
| Production Launch | Aug 17 | Aug 17 | 0 days |

# 7. RAID Management

RAID items are reviewed in weekly status meetings and daily during UAT/launch. Risk scoring uses Impact x Probability on a 1-5 scale. Scores of 15+ require executive visibility; launch blockers are escalated immediately.

| ID | Type | Description | Score | Owner | Mitigation / Resolution |
| --- | --- | --- | --- | --- | --- |
| R-01 | Risk | Payment certification delay | 15 | Engineering | Staging certification + backup processor plan |
| R-02 | Risk | Catalog data quality | 12 | Product | Validation rules + sample audit |
| I-01 | Issue | Three checkout defects in UAT | 20 | QA | Daily triage; critical defects fixed before gate |
| D-01 | Dependency | Security sign-off before deployment | 20 | Security | Reserved review window + evidence checklist |

# 8. Communications Plan

| Audience | Artifact / Meeting | Cadence | Purpose |
| --- | --- | --- | --- |
| Core delivery team | Stand-up / blocker review | Daily | Progress, blockers, dependencies |
| Workstream leads | Integrated plan review | 2x weekly | Schedule and cross-team coordination |
| Executive sponsor | Executive status update | Weekly | Health, decisions, risks, budget |
| QA/Product/Engineering | Defect triage | Daily during UAT | Prioritize and resolve defects |
| Launch team | Readiness review | T-3 days / T-1 day | Validate exit criteria and rollback readiness |

# 9. Change Control

Change requests document business rationale, scope/schedule/budget/quality impact, recommendation, approver, and decision. Approved changes are incorporated into the baseline and communicated to affected owners. Deferred changes are moved to the post-launch backlog.

| Change | Impact | Decision |
| --- | --- | --- |
| Guest checkout | +3 development days; absorbed within float | Approved |
| Second payment processor | +2 weeks; threatens launch baseline | Deferred |
| Add 500 SKUs | Higher catalog-quality risk | Approved as phased upload |

# 10. Quality & Launch Readiness

100% of critical checkout paths executed in UAT.

All critical and high-severity launch-blocking defects closed before readiness approval.

Payment authorization, capture, refund, and failure scenarios validated.

Security evidence package reviewed before production deployment.

Rollback steps, monitoring ownership, support runbook, and hypercare contacts confirmed.

# 11. KPI Framework & Outcome

| KPI | How Measured | Outcome |
| --- | --- | --- |
| Task completion | Completed / planned tasks by week | 12 -> 24 completed per week |
| Velocity | Weighted completed work per week | 24 -> 48 (+100%) |
| Issue health | Open and closed issues | 0 launch blockers at go-live |
| Milestone adherence | Actual vs baseline | Launch on baseline date |
| Budget variance | (Baseline - Actual) / Baseline | 1.7% favorable |
| Readiness | Gate criteria met / total | 100% critical criteria met |

# 12. Lessons Learned

Reserve external certification windows early because third-party dependencies can create schedule risk even when internal work is on track.

Daily defect triage during UAT reduces ambiguity and keeps ownership visible.

A single integrated tracker improves handoffs across product, engineering, QA, security, and operations.

Executive updates are most effective when they separate information from decisions required.

Catalog validation should begin before the full load to reduce late-cycle data-quality rework.

# 13. Portfolio Note

This is a simulated portfolio case study designed to demonstrate practical project coordination methods, artifacts, reporting, and analysis. Metrics and scenarios are intentionally realistic but are not presented as results from an employer or client engagement.