## Project Summary
Field | Details
Project Name | Global Leadership Training Rollout
Industry | Corporate HR
Objective | Deploy leadership program across 500 employees
Duration | 6 weeks
Role | Project Coordinator
Key Responsibilities | Milestone tracking, stakeholder coordination, reporting, risk management
Milestones Delivered | 100%
Timeline Variance | +2 days
Budget Variance | 3%
Stakeholder Satisfaction | 4.7 / 5

## Milestones
Milestone | Target Date | Owner | Status
Kickoff | Jan 3 | Coordinator | Complete
Requirements Complete | Jan 25 | BA | Complete
Integration | Feb 28 | Engineering | In Progress
Testing Complete | Mar 15 | QA | Planned
Go Live | Mar 30 | Leadership | Planned

## Risk Register
Risk | Impact | Likelihood | Mitigation | Owner
Vendor delay | High | Medium | Weekly sync | Ops
Scope creep | Medium | Medium | Change control | PMO
Resource shortage | High | Low | Backup staff | HR

## Issue Log
Issue | Impact | Owner | Resolution
API outage | Integration delay | Engineering | Escalated to vendor
Training delay | Program rollout risk | HR | Added additional session

## Change Log
Change ID | Description | Impact | Decision | Owner
CR1 | Extend testing | Timeline +3 days | Approved | PMO
CR2 | Add feature | Scope increase | Pending | Product

## Decision Log
Decision | Date | Owner | Outcome
Vendor selection | Feb 2 | CTO | Approved
Training schedule | Feb 10 | HR Director | Approved