## Slide 1
Global Leadership Training Rollout
Executive Program Update | Simulated Portfolio Case Study
Project coordination across North America, EMEA, APAC, and LATAM

## Slide 2
Executive Dashboard
Program closed Green across schedule, scope, quality, and budget
1,240
Target Leaders
1,132
Completed
96.6%
Attendance
97.6%
Completion
4.6/5
Satisfaction
45
Sessions
100%
Milestones
+1.3%
Budget Variance
0
Open Issues
Simulated portfolio case study | Global Leadership Training Rollout

## Slide 3
Scope & Operating Model
Governance
Charter, decisions, RAID, change control, executive updates
Content
Curriculum readiness and controlled regional localization
Technology
LMS configuration, enrollment logic, reporting
Delivery
Facilitator coverage, regional schedules, cohort execution
Communications
Participant messages, manager toolkit, reminders
Analytics
Attendance, completion, satisfaction, milestone and budget reporting
Simulated portfolio case study | Global Leadership Training Rollout

## Slide 4
Regional Performance
All four regions exceeded the simulated 95% completion threshold
Chart: 
| North America | EMEA | APAC | LATAM
Completion % | 98.5 | 97.4 | 97.1 | 97
98.5%
North America
97.4%
EMEA
97%+
APAC / LATAM
Simulated portfolio case study | Global Leadership Training Rollout

## Slide 5
Milestone Performance
Charter Approved
On time
Curriculum Baseline
On time
Localization
1 day late
LMS Ready
1 day early
Regional Delivery
On time
Executive Closeout
On time
100%
Milestones Complete
On Time
Final Closeout
Simulated portfolio case study | Global Leadership Training Rollout

## Slide 6
RAID & Issue Management
Highest-severity items were closed before program closeout
I-01 | Score 20 | Closed
LMS enrollment omission
D-01 | Score 16 | Complete
Regional HR sign-off dependency
R-02 | Score 15 | Closed
Localization delay risk
R-01 | Score 12 | Closed
Time-zone attendance risk
R-03 | Score 12 | Closed
Facilitator availability risk
Simulated portfolio case study | Global Leadership Training Rollout

## Slide 7
Budget Performance
Actual program cost finished below the simulated baseline
Chart: 
| Curriculum | Localization | LMS | Delivery | Comms | Evaluation
Baseline | 28000 | 22000 | 14000 | 42000 | 12000 | 10000
Actual | 27200 | 23150 | 13750 | 40800 | 11600 | 9800
$128K
Baseline
$126.3K
Actual
$1.7K
Favorable Variance
Simulated portfolio case study | Global Leadership Training Rollout

## Slide 8
Delivery & Participation Trend
Chart: 
| W1 | W2 | W3 | W4 | W5 | W6
Completions | 145 | 188 | 218 | 246 | 278 | 307
145 completions
Week 1
307 completions
Week 6
4.7 / 5
Satisfaction
Simulated portfolio case study | Global Leadership Training Rollout

## Slide 9
Change Control & Lessons Learned
Approved Changes
Approved second EMEA time slot
Extended recording access from 14 to 30 days
Added manager reinforcement guide
Lessons Learned
Plan time-zone coverage before participant communications
Prioritize localized content before full review
Maintain backup facilitators
Reconcile LMS enrollment against authoritative participant lists
Simulated portfolio case study | Global Leadership Training Rollout

## Slide 10
Closeout Summary
Program objectives were met in the simulated case study
96.6%
Attendance
97.6%
Completion
4.6/5
Satisfaction
+1.3%
Budget
Project Coordinator contribution
Coordinated global schedules, workstreams, stakeholders, risks, and changes.
Maintained formula-driven Excel reporting and executive status visibility.
Tracked participant delivery metrics and budget performance through closeout.
Simulated portfolio case study | Global Leadership Training Rollout