# Project Working Session - Meeting Notes

Week 4 | Simulated Portfolio Case Study

| Date | Facilitator | Participants | Purpose |
| --- | --- | --- | --- |
| May 15, 2026 | Project Coordinator | L&D, Regional HR, LMS, Communications | Review regional delivery readiness, issues, and actions |

# Agenda

Regional delivery status

LMS enrollment reconciliation

Facilitator coverage

Attendance risk

Communications

RAID and change review

# Discussion Summary

North America delivery remained on plan. EMEA and APAC schedules were confirmed, while the team reviewed the corrected LMS enrollment logic and the backup facilitator pool. LATAM communications were approved for release after final regional validation.

# Decisions

| Decision ID | Decision | Owner | Date |
| --- | --- | --- | --- |
| DEC-04 | Retain second EMEA session window | Project Coordinator | May 15, 2026 |
| DEC-05 | Use backup facilitator pool for schedule resilience | L&D Lead | May 15, 2026 |
| DEC-06 | Proceed with LATAM communications after regional validation | Regional HR Lead | May 15, 2026 |

# Action Items

| Action | Owner | Due | Status |
| --- | --- | --- | --- |
| Reconcile LMS manager population | LMS Administrator | May 18, 2026 | Complete |
| Confirm APAC facilitator backups | L&D Lead | May 18, 2026 | Complete |
| Release LATAM participant communication | HR Communications | May 20, 2026 | Complete |
| Update dashboard with Week 4 results | Project Coordinator | May 18, 2026 | Complete |

# RAID Review

No new critical risks were identified. Existing localization and facilitator risks remained controlled. The LMS enrollment issue was assigned for immediate correction and reconciliation.