# Weekly Status Report - Week 6

Global Leadership Training Rollout | Simulated Portfolio Case Study

| Overall Status | Schedule | Budget | Scope | Quality |
| --- | --- | --- | --- | --- |
| Green | Green | Green | Green | Green |

# Executive Summary

The global leadership training rollout completed all planned regional delivery and entered closeout. All six milestones are complete, no risks or issues remain open, and final program performance exceeded the attendance, completion, and satisfaction targets.

# Key Performance Indicators

| KPI | Current | Target / Baseline | Status |
| --- | --- | --- | --- |
| Target leaders | 1,240 | 1,240 | Complete |
| Completed leaders | 1,132 | >=95% of attendees | Met |
| Attendance rate | 96.6% | >=95% | Met |
| Completion rate | 97.6% | >=95% | Met |
| Average satisfaction | 4.6 / 5 | >=4.3 / 5 | Met |
| Sessions delivered | 45 | 45 | Complete |
| Budget | $126,300 | $128,000 | 1.3% favorable |

# Completed This Week

Completed final LATAM cohort reconciliation.

Closed remaining RAID items.

Validated final budget actuals.

Prepared executive closeout package.

Consolidated lessons learned and participant feedback.

# Next Steps

Deliver executive closeout update.

Archive project artifacts and final decision log.

Transition ongoing leadership-program ownership to L&D operations.

# Decisions / Escalations

No executive escalations are required. Final closeout approval is the remaining governance action.